## Slide 1: Semantic layer Planning next steps
05 Oct, 2022

## Slide 2: Contents
1. |  | Semantic Layer – path to future state architecture
2. |  | Approach
3. |  | High Level Plan v0.1
4. |  | Semantic Layer Team: Current Hypothesis to be refined during workshops
5. |  | Semantic Layer Vision: A key next step is building out the next level of detail
1
2
3
4
5

## Slide 3: Semantic Layer – path to future state architecture
Vision
?
Requirements
?
MVP
?
Strategic
End-Solution
?
1
2
3
4
Today
RAFT scope
May 23
The key stages we need to follow in order to agree the future state Semantic Layer (SL) architecture is as follows:

## Slide 4: Approach
Vision
Obtain Data integration decision tree
Agreed Use cases
Define Business goals/outcomes
Define SL source and consumer systems/feeds
Define Business/client users
1
Requirements for strategic solution
Requirements for MVP solution
Defined SL data sources and consumers of data
Requirements
2
RAFT requirements (including Complex Calculators and Models)
Other business requirements (e.g. Quants, Client Servicing etc)
MVP
3
Prioritised business requirements reviewed
Technical requirements for prioritised set
Functional requirements for prioritised set
Strategic
End solution
4
Outputs
Outputs
Inputs
Inputs
Input into
Input into
Input into
Input into
Input into
Input into
Align to vision, lessons learnt so far and agree ways of working
Agreed bare bone “Must have” architecture
Enhance roadmap
Identify solution gaps
Outputs
Agreed strategic architecture
Enhance roadmap
Identify solution gaps
Prioritised business requirements
RAFT 5658 – PRC reports
Define roadmap
Workshop (RAFT) to prioritize requirements
Workshop (f2f) to agree MVP architecture
Agreed req deliverables, constraints, req owners
Agreed SL deliverables, tech constraints, owners, delivery team
Attendees (TBD): Sandie, 2xArchitects, Lead developer(s)
Attendees (TBD): IT Manager, Architects, Developers, Analyst
Factor in Data Gov and e.g Calibra
Anitha, Jamie, Chad, Roger
Data Governance

## Slide 5: High Level Plan v0.1
# | Stage | Activity | w/c 04/10 | w/c 10/1 | w/c 17/24 | w/c 24/10 | w/c 31/10 | w/c 7/11 | w/c 14/11 | 21/11 | w/c 28/11 | w/c 05/12 | Dec +
1.1 | Vision | Obtain Data integration decision tree |  |  |  |  |  |  |  |  |  |  | 
1.2 |  | Define Snowflake source and consumer systems/feeds |  |  |  |  |  |  |  |  |  |  | 
1.3 |  | Define Business goals/outcomes |  |  |  |  |  |  |  |  |  |  | 
1.4 |  | Define Business/client users |  |  |  |  |  |  |  |  |  |  | 
1.5 |  | Agree design principles for MVP solution |  |  |  |  |  |  |  |  |  |  | 
1.6 |  | Agree design principles for strategic solution |  |  |  |  |  |  |  |  |  |  | 
1.7 |  | Agree Vision and ways of working |  |  |  |  |  |  |  |  |  |  | 
2.1 | Requirements | Categorise RAFT requirements (tactical/strategic) |  |  |  |  |  |  |  |  |  |  | 
2.2 |  | Analysis of Complex Calculators and Models |  |  |  |  |  |  |  |  |  |  | 
2.3 |  | Investigate Feat-5658 and obtain lessons learned |  |  |  |  |  |  |  |  |  |  | 
2.4 |  | Identify non RAFT requirements and owners |  |  |  |  |  |  |  |  |  |  | 
2.5 |  | Prioritise RAFT business requirements (workshop) |  |  |  |  |  |  |  |  |  |  | 
2.6 |  | Prioritise Non RAFT business requirements (strategic) |  |  |  |  |  |  |  |  |  |  | 
2.7 |  | For RAFT priority requirements, review solution intent, owners, problem, DoD, TAC etc |  |  |  |  |  |  |  |  |  |  | 
2.8 |  | Develop functional requirements for prioritised reqs |  |  |  |  |  |  |  |  |  |  | 
2.9 |  | Develop technical requirements for prioritised reqs |  |  |  |  |  |  |  |  |  |  | 
3.1 | MVP | Define and agree bare bone “Must have” architecture (workshop) |  |  |  |  |  |  |  |  |  |  | 
3.2 |  | Identify solution gaps |  |  |  |  |  |  |  |  |  |  | 
3.3 |  | Enhance roadmap |  |  |  |  |  |  |  |  |  |  | 
4.1 | Strategic Solution | Define and agree strategic architecture |  |  |  |  |  |  |  |  |  |  | 
4.2 |  | Identify solution gaps |  |  |  |  |  |  |  |  |  |  | 
4.3 |  | Enhance roadmap |  |  |  |  |  |  |  |  |  |  | 
Activities to focus on NL visit
On track
Completed
Factor in Data Gov and e.g Calibra

## Slide 6: Semantic Layer Team: Current Hypothesis to be refined during workshops
Head of IT (Europe) Ross Macleod
Technical Delivery Manager
Vas Lappas
Product Owner / Scrum Master
Data Modeller
Business Data Architect
(Tom Finlay?)
Snowflake Developer
Snowflake Developer
Collibra Analyst
Aladdin SME
ADC SME
Snowflake SME
Catalin Bobarnac
Data Architect
Business Data Architect Paul Huizinga
RAFT IT Workstream Lead
Sandie Lovie
Product Owner (Data Extracts)
?
Product Owner (Interfaces) Maarten Winter
Team Members
Team Members
CDO
Lance Cameron
Nicole Sandig
CTO / RAFT Steerco
Solution Architect
Jamie de Kruif
Product Management
Sarah Tjaden
Miguel Pereira
Lead Developer
Snowflake Admin
Chad Good
Snowflake Admin
Shrini Addagarla
In Place
Potential Gap
Key
Notes
Potential Gaps are roles not resources – one resource may be able to cover multiple roles (existing resources might already be able to cover some of these roles)
This initial hypothesis will be reviewed and refined in workshops with both architects and developers over the next days
Graham Hopper
Lead Developer
SMEs
Core team

## Slide 7: Semantic Layer Vision: A key next step is building out the next level of detail
ETL
Clearwater
ABOR
Other
Aladdin Data Cloud
IBOR
Semantic Data Layer (Snowflake)
Reporting
IBOR Consumers
ABOR Consumers
Collibra
Collibra data catalog
Use case 1
Self Service reporting and analytics
Use case 2
Client Reporting
Use case 3
Data distribution hub for key internal systems, clients and vendors
Use case 4
Data Science Platform
Outbound Feeds
Legacy Reporting
Self Service BI
Domain based Analytics
ComplySci
DSMSABIC
FINSCAN
Clearwater
BlackRock
Citi
Internal systems
External systems
To be defined and agreed
Portfolio Management
Quants
Accounting
Other
KnowledgeLake
Other
MUREX
Trade order files
MEDM
Other
Use case 5
Other
To be defined
Who is best to provide?
To be completed
Key Notes
This diagram represents an initial high level representation of the Semantic Layer
To complete this view we will require the following:
  Identification of Use cases
  Complete listing of all inbound sources and outbound feeds and consumers of data
  Resourcing delivery team
  Identification and prioritisation of requirements
To be fully documented
Principles
High quality, controlled and trusted data
Common business definitions across business
Enhanced user access controls
tbd